## Milestones
TCO AUTOMATION SYSTEM - PHASE 2 PROJECT PLAN
Total Duration: 54 weeks (254 days) ¦ 9 Milestones ¦ 40 Tasks ¦ Estimated Effort: 259 person-days
Milestone | Name | Phase | Timeline (Weeks) | Duration (Days) | Key Activities | Deliverables | Exit Criteria | Dependencies | Team Size | Critical Path | Risk Level | Payment % | Status
DISCOVERY: Requirements gathering, analysis, and planning
M0 | Discovery & Requirements Complete | Discovery | W1-W5 (5 weeks) | 24 | • Historical proposal inventory (500+ files) • TCO template variant collection & analysis • Vendor document pattern analysis (FIS, JH, CSI) • Volume & performance requirements definition • Technical architecture design (C4 diagrams) • Risk assessment & mitigation planning • Discovery exit review & go/no-go decision | • DD1: Historical Proposal Inventory (Excel + metadata) • DD2: TCO Template Catalog & Mapping Specs • DD3: Vendor Pattern Analysis Report • DD4: Requirements Specification (SLAs, NFRs) • DD5: Technical Architecture Document + C4 Diagrams • DD6: Risk Register with mitigation plans • DD7: Discovery Exit Report + Signed Acceptance | • All discovery questions answered (100%) • Historical inventory complete (file count, formats, vendors) • All TCO template variants cataloged (min 3-5) • Vendor extraction accuracy baseline established (≥95%) • Technical architecture approved by client IT • Risk register reviewed (min 15-20 risks) • Client stakeholder sign-off on findings • Dev phase work packages validated | Project kickoff | 4-5 (PM, Tech Lead, BA, Developer, Client SME) | YES | High | 10% | Not Started
DEVELOPMENT - CORE: Foundation infrastructure and core processing engine
M1 | Foundation Infrastructure Operational | Development - Core | W6-W11 (6 weeks) | 30 | • PostgreSQL database implementation (schema, migrations) • Celery + RabbitMQ queue system setup • Configuration management & secrets vault • Structured logging infrastructure (ELK/CloudWatch) • FastAPI REST framework with authentication • Infrastructure testing & validation • Performance baseline testing | • D1: PostgreSQL database + ORM models + migrations • D2: Celery + RabbitMQ job queue (4 workers) • D3: Configuration management system + secrets vault • D4: Structured logging framework + aggregation • D5: FastAPI application + Swagger documentation • D6: Infrastructure test suite (unit + integration) • D7: Infrastructure setup guide + runbook | • Database operational with all tables created • Queue system processing test jobs successfully • API endpoints returning 200 OK (health checks) • Logs aggregating in centralized system • No hardcoded secrets in codebase (Git audit clean) • Infrastructure tests passing (≥80% coverage) • Performance baseline documented | M0 (Discovery complete) | 4 (Backend Dev, DevOps, DBA, Tech Lead) | YES | Medium | - | Not Started
M2 | Batch Processing Engine Live | Development - Core | W12-W16 (5 weeks) | 24 | • Bulk import & queue management implementation • Parallel worker pool (4-8 workers) • Error handling & retry logic with dead letter queue • Real-time progress tracking (WebSocket) • Volume testing (20+ proposals) • Integration with extraction pipeline • Performance optimization | • D8: Bulk import system + directory watcher • D9: Worker pool infrastructure (scalable) • D10: Error handling framework + dead letter queue • D11: Progress tracking API + dashboard • D12: Batch processing integration tests • D13: Volume test report (20-proposal baseline) • D14: Batch processing user guide | • 20 proposals processed successfully in batch • Avg processing time ≤90 seconds per proposal • Workers stable (no crashes under load) • Error handling tested (retry + dead letter queue) • Progress tracking real-time (5-sec updates) • Integration tests passing (E2E workflows) • Performance meets SLA (defined in M0) | M1 (Infrastructure ready) | 3 (Backend Dev, QA, DevOps) | YES | High | - | Not Started
DEVELOPMENT - FEATURES: Feature development and enhancements
M3 | Multi-Template Support Enabled | Development - Features | W17-W22 (6 weeks) | 30 | • Template registry & versioning system • Dynamic field mapping engine • Template auto-detection (≥95% accuracy) • Template management web UI (no-code) • Multi-template testing (3+ variants) • Template configuration documentation • User training materials | • D15: Template registry database + versioning • D16: Dynamic mapping engine + config schema • D17: Template detection algorithm (ML-based) • D18: Template management web UI • D19: Multi-template test suite (3+ templates) • D20: Template configuration guide • D21: Template admin training materials | • Min 3 template variants configured in registry • Template auto-detection ≥95% accurate • Dynamic mapping working for all templates • Non-developer can upload & configure template via UI • Template switching tested (same proposal → different templates) • Template versioning working (rollback tested) • Template admin trained and certified | M2 (Batch processing working) | 4 (Full Stack Dev, UX Designer, BA, QA) | No | Medium | - | Not Started
M4 | Historical Processing Complete | Development - Features | W23-W28 (6 weeks) | 26 | • Historical import CLI tool development • Document classification (vendor + format detection) • Legacy format handlers (OCR for scanned PDFs) • De-duplication & historical analysis • Mass import of historical proposals (100+) • Data quality validation & cleanup • Historical insights dashboard | • D22: Historical import CLI tool • D23: Classification engine (vendor + format) • D24: Legacy format handlers (OCR pipeline) • D25: De-duplication engine + analytics • D26: Historical proposals database (100+ files) • D27: Data quality report • D28: Historical insights dashboard | • Min 100 historical proposals imported successfully • Vendor classification ≥90% accurate • OCR accuracy ≥85% on scanned documents • Duplicates identified and resolved • Historical data quality validated (completeness check) • Historical pricing trends analyzed • Insights dashboard showing historical patterns | M2 (Batch processing), M3 (Multi-template) | 4 (Developer, ML Engineer, Data Analyst, QA) | No | High | 25% | Not Started
M5 | Exception Management & Review Workflow Live | Development - Features | W29-W34 (6 weeks) | 28 | • Review queue backend implementation • Web-based review UI (side-by-side comparison) • Approval workflow & state machine • Feedback loop & active learning • Review workflow testing (E2E) • Reviewer training & certification • SLA tracking & notifications | • D29: Review queue backend + API • D30: Review web UI (intuitive, non-technical) • D31: Approval workflow engine + state machine • D32: Feedback loop system + learning pipeline • D33: Review workflow integration tests • D34: Reviewer training materials • D35: Review SLA dashboard | • Review queue operational (items auto-routed) • Review UI tested by non-technical users • Approval workflow tested (multi-level) • Feedback loop capturing corrections • Review SLA tracking working (24-hour alerts) • Min 3 reviewers trained and certified • Review throughput ≥10 items/hour (per reviewer) | M2 (Batch processing) | 5 (Full Stack Dev, UX, Backend Dev, BA, QA) | YES | Medium | - | Not Started
DEVELOPMENT - OPERATIONS: Monitoring, reporting, and operational readiness
M6 | Monitoring, Reporting & Analytics Operational | Development - Operations | W35-W41 (7 weeks) | 31 | • Real-time operations dashboard • Email & Slack notification system • Standard reports library (7+ reports) • Enhanced audit trail (compliance) • Monitoring & alerting testing • Report scheduling & automation • Stakeholder training on dashboards | • D36: Operations dashboard (real-time) • D37: Notification system (Email + Slack) • D38: Report library (7+ standard reports) • D39: Enhanced audit trail system • D40: Monitoring integration tests • D41: Report catalog & user guide • D42: Dashboard training materials | • Dashboard shows real-time system health • Notifications working (job complete, failures, SLA) • All 7 standard reports generating successfully • Audit trail tracks all critical operations • Monitoring alerts tested (simulate failures) • Reports scheduled (weekly automated delivery) • Stakeholders trained on dashboards | M2 (Batch), M5 (Review) | 4 (Full Stack Dev, Data Engineer, DevOps, BA) | No | Low | - | Not Started
QUALITY ASSURANCE: Testing, validation, and client acceptance
M7 | Testing Complete & UAT Sign-off | Quality Assurance | W42-W48 (7 weeks) | 34 | • Unit test expansion (≥80% coverage) • Integration testing (E2E scenarios) • Volume & performance testing (20+ proposals) • User Acceptance Testing with client • Bug fixing & retesting (P0, P1 issues) • Performance optimization • UAT sign-off & approval | • D43: Unit test suite (≥80% coverage) • D44: Integration test suite (15+ scenarios) • D45: Performance test report (load testing) • D46: UAT test plan (20+ scenarios) • D47: Bug fix report (all P0/P1 resolved) • D48: UAT test results & sign-off • D49: Go-live readiness checklist | • Unit test coverage ≥80% • All integration tests passing • 20-proposal batch processed in <30 min • Client UAT scenarios executed (100%) • All P0 and P1 bugs resolved • Client formal UAT sign-off obtained • Go-live checklist 100% complete | M1-M6 (All dev complete) | 5 (QA, Performance Eng, Developers, Client Users) | YES | High | 25% | Not Started
DEPLOYMENT: Documentation, training, and production deployment
M8 | Documentation, Training & Go-Live | Deployment | W49-W54 (6 weeks) | 27 | • Technical documentation (Architecture, API, Dev) • Operations manual & runbooks • End-user documentation & videos • Knowledge transfer training (3 tracks) • Production deployment preparation • Go-live execution & cutover • Post-go-live support (2 weeks) | • D50: Technical Documentation (ReadTheDocs) • D51: Operations Manual + Runbooks • D52: User Guide + Video Tutorials (5+) • D53: Training materials (Admin, User, Developer) • D54: Training completion certificates • D55: Deployment guide + checklist • D56: Go-live sign-off & warranty start | • All documentation complete and reviewed • Min 80% of users trained and certified • Production environment validated • Go-live checklist 100% complete • System operational in production • Client final acceptance signed • 2-week stabilization period complete | M7 (UAT sign-off) | 6 (Tech Writer, Trainer, Tech Lead, PM, DevOps, Support) | YES | Medium | 25% | Not Started
PROJECT SUMMARY & KEY METRICS
Total Milestones: | 9 | Critical Path Milestones: | M0, M1, M2, M5, M7, M8
Total Duration: | 54 weeks (254 days) | Total Payment Points: | 85%
Phase Count: | 6 phases | Estimated Team: | 8-10 resources (peak)
Total Deliverables: | 63 items | High Risk Milestones: | 4

## Work Packages
WP | Task ID | Task Name | Description | Deliverable | Dependencies | Status
WP1 | 1.1 | Database Schema Design | Design data model for proposals, extractions, outputs | Schema docs | - | Not Started
WP1 | 1.2 | Job Queue Implementation | Implement job submission and tracking | Queue module | 1.1 | Not Started
WP1 | 1.3 | Configuration Management | Environment-based settings | Config module | - | Not Started
WP1 | 1.4 | Logging Infrastructure | Structured logging with rotation | Logging module | - | Not Started
WP2 | 2.1 | Queue Management System | Proposal ingestion and queue | Queue manager | WP1 | Not Started
WP2 | 2.2 | Parallel Worker Implementation | Worker pool management | Worker module | 2.1 | Not Started
WP2 | 2.3 | Error Handling & Retry | Retry logic and dead letter queue | Error handling | 2.2 | Not Started
WP2 | 2.4 | Progress Tracking | Real-time progress updates | Progress API | 2.2 | Not Started
WP3 | 3.1 | Template Storage & Versioning | Template registry structure | Registry module | WP1 | Not Started
WP3 | 3.2 | Dynamic Mapping Engine | Field-to-cell mapping | Mapping engine | 3.1 | Not Started
WP3 | 3.3 | Template Detection Logic | Auto-match templates | Detection module | 3.2 | Not Started
WP3 | 3.4 | Configuration UI | Template management interface | Config UI | 3.3 | Not Started
WP4 | 4.1 | Bulk Import Utility | Directory scanner and importer | Import CLI | WP1 | Not Started
WP4 | 4.2 | Document Classification | Vendor and format detection | Classifier | 4.1 | Not Started
WP4 | 4.3 | Legacy Format Handlers | Support for older formats | Legacy extractors | 4.2 | Not Started
WP4 | 4.4 | De-duplication Logic | Identify and handle duplicates | De-dup module | 4.2 | Not Started
WP5 | 5.1 | Review Queue Backend | Exception queue data model | Queue backend | WP2, WP3 | Not Started
WP5 | 5.2 | Web-based Review UI | Review interface | Review UI | 5.1 | Not Started
WP5 | 5.3 | Approval Workflow | Approval state machine | Workflow engine | 5.2 | Not Started
WP5 | 5.4 | Feedback Loop Integration | Learning from corrections | Feedback module | 5.3 | Not Started
WP6 | 6.1 | Status Dashboard | Real-time status display | Dashboard | WP2 | Not Started
WP6 | 6.2 | Notification System | Email/Slack notifications | Notifications | WP2 | Not Started
WP6 | 6.3 | Analytics & Reporting | Standard reports | Reports module | WP5 | Not Started
WP6 | 6.4 | Audit Trail Enhancement | Extended audit logging | Audit module | WP5 | Not Started
WP7 | 7.1 | Unit Test Expansion | 80% code coverage | Test suite | WP1-WP6 | Not Started
WP7 | 7.2 | Integration Testing | End-to-end tests | Integration tests | 7.1 | Not Started
WP7 | 7.3 | Volume Testing | 20+ proposal stress test | Volume report | 7.2 | Not Started
WP7 | 7.4 | User Acceptance Testing | UAT execution | UAT sign-off | 7.3 | Not Started
WP8 | 8.1 | Technical Documentation | Architecture and API docs | Tech docs | WP7 | Not Started
WP8 | 8.2 | Operations Manual | Daily operations procedures | Ops manual | WP7 | Not Started
WP8 | 8.3 | User Guides | End-user documentation | User guides | WP7 | Not Started
WP8 | 8.4 | Knowledge Transfer | Training sessions | Training materials | 8.1-8.3 | Not Started

## Risk Register
ID | Risk Description | Probability | Impact | Score | Mitigation | Owner | Status
R1 | Historical documents in unknown formats | Medium | High | High | Early discovery phase with sample analysis | Tech Lead | Open
R2 | TCO template variations more complex than expected | Medium | Medium | Medium | Flexible mapping engine with fallback options | Developer | Open
R3 | Volume exceeds capacity | Low | Medium | Low | Scalable architecture with parallel processing | Tech Lead | Open
R4 | Key resource unavailable | Medium | Medium | Medium | Cross-training; documentation | PM | Open
R5 | Client SME availability | Medium | High | High | Early scheduling; async communication | PM | Open
R6 | Integration dependencies | Low | Medium | Low | Modular design with clear APIs | Tech Lead | Open
R7 | Performance bottlenecks | Medium | Medium | Medium | Early performance testing; optimization sprints | Developer | Open
R8 | Scope creep | Medium | High | High | Change control process; clear SOW | PM | Open

## Acceptance Criteria
ID | Type | Criteria | Target | Validation Method | Status
AC1 | Functional | System processes 20+ proposals per month | - | Volume test with real proposals | Not Tested
AC2 | Functional | Historical proposals imported with >90% success rate | >90% | Batch processing report | Not Tested
AC3 | Functional | All TCO template variants supported via configuration | 100% | Template coverage test | Not Tested
AC4 | Functional | Exception queue enables manual review with resolution tracking | - | Workflow walkthrough | Not Tested
AC5 | Functional | Monitoring dashboard shows real-time status and alerts | - | UI demonstration | Not Tested
PA1 | Performance | Single proposal processing time | < 2 minutes | Timing test | Not Tested
PA2 | Performance | Batch of 20 proposals | < 30 minutes | Batch timing test | Not Tested
PA3 | Performance | Dashboard response time | < 3 seconds | UI response test | Not Tested
PA4 | Performance | System availability | 99% | Uptime monitoring | Not Tested
QA1 | Quality | Extraction accuracy (auto-accepted) | > 95% | Accuracy report | Not Tested
QA2 | Quality | Overall processing success rate | > 98% | Processing report | Not Tested
QA3 | Quality | Zero data loss or corruption | 100% | Data integrity check | Not Tested
QA4 | Quality | Complete audit trail for all outputs | 100% | Audit log review | Not Tested