## Milestones
Milestone | Description | Work Package | Deliverables | Exit Criteria | Payment % | Status
M0 | Discovery Complete | Discovery Phase | DD1-DD6 | Discovery exit criteria met | 10% | Not Started
M1 | Foundation Complete | WP1 | Database, Queue, Config, Logging | Infrastructure operational | - | Not Started
M2 | Batch Processing Operational | WP2 | D1, D2 | 20 proposals processed successfully | - | Not Started
M3 | Multi-Template Support | WP3 | D3 | All templates configured | - | Not Started
M4 | Historical Processing Ready | WP4 | D4 | Historical import complete | 25% | Not Started
M5 | Exception Management Live | WP5 | D5 | Review workflow operational | - | Not Started
M6 | Monitoring & Reporting | WP6 | D6, D7 | Dashboard and reports live | - | Not Started
M7 | Testing Complete | WP7 | Test Reports | UAT sign-off | 25% | Not Started
M8 | Documentation & Go-Live | WP8 | D8-D15 | Final acceptance | 25% | Not Started

## Work Packages
WP | Task ID | Task Name | Description | Deliverable | Dependencies | Status
WP1 | 1.1 | Database Schema Design | Design data model for proposals, extractions, outputs | Schema docs | - | Not Started
WP1 | 1.2 | Job Queue Implementation | Implement job submission and tracking | Queue module | 1.1 | Not Started
WP1 | 1.3 | Configuration Management | Environment-based settings | Config module | - | Not Started
WP1 | 1.4 | Logging Infrastructure | Structured logging with rotation | Logging module | - | Not Started
WP2 | 2.1 | Queue Management System | Proposal ingestion and queue | Queue manager | WP1 | Not Started
WP2 | 2.2 | Parallel Worker Implementation | Worker pool management | Worker module | 2.1 | Not Started
WP2 | 2.3 | Error Handling & Retry | Retry logic and dead letter queue | Error handling | 2.2 | Not Started
WP2 | 2.4 | Progress Tracking | Real-time progress updates | Progress API | 2.2 | Not Started
WP3 | 3.1 | Template Storage & Versioning | Template registry structure | Registry module | WP1 | Not Started
WP3 | 3.2 | Dynamic Mapping Engine | Field-to-cell mapping | Mapping engine | 3.1 | Not Started
WP3 | 3.3 | Template Detection Logic | Auto-match templates | Detection module | 3.2 | Not Started
WP3 | 3.4 | Configuration UI | Template management interface | Config UI | 3.3 | Not Started
WP4 | 4.1 | Bulk Import Utility | Directory scanner and importer | Import CLI | WP1 | Not Started
WP4 | 4.2 | Document Classification | Vendor and format detection | Classifier | 4.1 | Not Started
WP4 | 4.3 | Legacy Format Handlers | Support for older formats | Legacy extractors | 4.2 | Not Started
WP4 | 4.4 | De-duplication Logic | Identify and handle duplicates | De-dup module | 4.2 | Not Started
WP5 | 5.1 | Review Queue Backend | Exception queue data model | Queue backend | WP2, WP3 | Not Started
WP5 | 5.2 | Web-based Review UI | Review interface | Review UI | 5.1 | Not Started
WP5 | 5.3 | Approval Workflow | Approval state machine | Workflow engine | 5.2 | Not Started
WP5 | 5.4 | Feedback Loop Integration | Learning from corrections | Feedback module | 5.3 | Not Started
WP6 | 6.1 | Status Dashboard | Real-time status display | Dashboard | WP2 | Not Started
WP6 | 6.2 | Notification System | Email/Slack notifications | Notifications | WP2 | Not Started
WP6 | 6.3 | Analytics & Reporting | Standard reports | Reports module | WP5 | Not Started
WP6 | 6.4 | Audit Trail Enhancement | Extended audit logging | Audit module | WP5 | Not Started
WP7 | 7.1 | Unit Test Expansion | 80% code coverage | Test suite | WP1-WP6 | Not Started
WP7 | 7.2 | Integration Testing | End-to-end tests | Integration tests | 7.1 | Not Started
WP7 | 7.3 | Volume Testing | 20+ proposal stress test | Volume report | 7.2 | Not Started
WP7 | 7.4 | User Acceptance Testing | UAT execution | UAT sign-off | 7.3 | Not Started
WP8 | 8.1 | Technical Documentation | Architecture and API docs | Tech docs | WP7 | Not Started
WP8 | 8.2 | Operations Manual | Daily operations procedures | Ops manual | WP7 | Not Started
WP8 | 8.3 | User Guides | End-user documentation | User guides | WP7 | Not Started
WP8 | 8.4 | Knowledge Transfer | Training sessions | Training materials | 8.1-8.3 | Not Started

## Risk Register
ID | Risk Description | Probability | Impact | Score | Mitigation | Owner | Status
R1 | Historical documents in unknown formats | Medium | High | High | Early discovery phase with sample analysis | Tech Lead | Open
R2 | TCO template variations more complex than expected | Medium | Medium | Medium | Flexible mapping engine with fallback options | Developer | Open
R3 | Volume exceeds capacity | Low | Medium | Low | Scalable architecture with parallel processing | Tech Lead | Open
R4 | Key resource unavailable | Medium | Medium | Medium | Cross-training; documentation | PM | Open
R5 | Client SME availability | Medium | High | High | Early scheduling; async communication | PM | Open
R6 | Integration dependencies | Low | Medium | Low | Modular design with clear APIs | Tech Lead | Open
R7 | Performance bottlenecks | Medium | Medium | Medium | Early performance testing; optimization sprints | Developer | Open
R8 | Scope creep | Medium | High | High | Change control process; clear SOW | PM | Open

## Acceptance Criteria
ID | Type | Criteria | Target | Validation Method | Status
AC1 | Functional | System processes 20+ proposals per month | - | Volume test with real proposals | Not Tested
AC2 | Functional | Historical proposals imported with >90% success rate | >90% | Batch processing report | Not Tested
AC3 | Functional | All TCO template variants supported via configuration | 100% | Template coverage test | Not Tested
AC4 | Functional | Exception queue enables manual review with resolution tracking | - | Workflow walkthrough | Not Tested
AC5 | Functional | Monitoring dashboard shows real-time status and alerts | - | UI demonstration | Not Tested
PA1 | Performance | Single proposal processing time | < 2 minutes | Timing test | Not Tested
PA2 | Performance | Batch of 20 proposals | < 30 minutes | Batch timing test | Not Tested
PA3 | Performance | Dashboard response time | < 3 seconds | UI response test | Not Tested
PA4 | Performance | System availability | 99% | Uptime monitoring | Not Tested
QA1 | Quality | Extraction accuracy (auto-accepted) | > 95% | Accuracy report | Not Tested
QA2 | Quality | Overall processing success rate | > 98% | Processing report | Not Tested
QA3 | Quality | Zero data loss or corruption | 100% | Data integrity check | Not Tested
QA4 | Quality | Complete audit trail for all outputs | 100% | Audit log review | Not Tested