## Milestones
Milestone | Description | Work Package | Deliverables | Exit Criteria | Payment % | Status
M0 | Discovery Complete | Discovery Phase | DD1-DD6 | Discovery exit criteria met | 10% | Not Started
M1 | Foundation Complete | WP1 | Database, Queue, Config, Logging | Infrastructure operational | - | Not Started
M2 | Batch Processing Operational | WP2 | D1, D2 | 20 proposals processed successfully | - | Not Started
M3 | Multi-Template Support | WP3 | D3 | All templates configured | - | Not Started
M4 | Historical Processing Ready | WP4 | D4 | Historical import complete | 25% | Not Started
M5 | Exception Management Live | WP5 | D5 | Review workflow operational | - | Not Started
M6 | Monitoring & Reporting | WP6 | D6, D7 | Dashboard and reports live | - | Not Started
M7 | Testing Complete | WP7 | Test Reports | UAT sign-off | 25% | Not Started
M8 | Documentation & Go-Live | WP8 | D8-D15 | Final acceptance | 25% | Not Started

## Work Packages
WP | Task ID | Task Name | Description | Detailed Activities | Deliverable | Dependencies | Effort (Days) | Resources | Key Risks | Acceptance Criteria | Status
WP0 | 0.1 | Historical Proposal Inventory | Catalog all historical proposals: file count, formats, vendors, date ranges | • Scan client file systems for proposal documents • Categorize by vendor (FIS, Jack Henry, CSI, Fiserv, etc.) • Identify file formats (Word, Excel, PDF, scanned images) • Document naming conventions and folder structures • Assess file sizes and complexity (page counts, table counts) • Create inventory spreadsheet with metadata • Identify corrupted or inaccessible files • Estimate extraction complexity scoring (1-5 scale) | Historical_Proposal_Inventory.xlsx (with metadata: vendor, format, date, pages, complexity score) | - | 3 | BA + Client SME | • Files scattered across multiple locations/systems • Missing metadata (no clear vendor/date identification) • Legacy formats no longer supported • Access permissions/security restrictions | • 100% of accessible proposal files cataloged • Each file tagged with: vendor, format, date, page count • Complexity scores assigned (based on table count, layout) • Client SME validation of inventory completeness • Sample files extracted for each vendor/format combination | Not Started
WP0 | 0.2 | TCO Template Variants Collection | Gather all TCO output template variants and document differences | • Collect all Excel TCO templates currently in use • Document template versioning and evolution history • Map field differences between template versions • Identify client-specific customizations • Document formula logic in each template • Extract column mappings and cell coordinates • Analyze conditional formatting and validation rules • Create template taxonomy and decision tree | TCO_Template_Catalog.xlsx + Template_Mapping_Specifications.docx | - | 4 | Developer + Client SME | • Undocumented template modifications over time • Complex formulas with unclear business logic • Client-specific templates not shared initially • Template versions incompatible with current automation | • All template variants collected (min 3-5 expected) • Field-by-field mapping documented for each template • Formula logic reverse-engineered and documented • Decision criteria for template selection defined • Backward compatibility assessment completed | Not Started
WP0 | 0.3 | Vendor Document Pattern Analysis | Analyze proposal patterns for each vendor to optimize extraction strategies | • Select representative samples (3-5 per vendor) • Manual extraction from samples to establish baseline • Document table structures and layouts per vendor • Identify vendor-specific terminology mappings • Test current extraction methods on samples • Measure accuracy of rule-based vs AI extraction • Document extraction failure patterns • Assess need for vendor-specific extraction rules • Evaluate direct PDF vs hybrid extraction methods | Vendor_Pattern_Analysis.docx + Extraction_Accuracy_Baseline.xlsx | 0.1 | 5 | Developer + Data Analyst | • Vendor document formats change over time (no consistency) • Sample size too small to capture all variations • Current extraction accuracy lower than expected (<90%) • Complex layouts require hybrid/manual extraction | • Min 3 samples per vendor analyzed (FIS, JH, CSI at minimum) • Extraction accuracy baseline established (target ≥95%) • Vendor terminology dictionary created for each vendor • Recommended extraction strategy documented per vendor • Known failure scenarios cataloged with workarounds | Not Started
WP0 | 0.4 | Volume & Performance Requirements Definition | Define SLAs, volume projections, and performance requirements | • Document current manual processing times per proposal • Define monthly volume projections (current + 12 months) • Establish performance SLAs (processing time per proposal) • Define accuracy SLAs (extraction accuracy targets) • Document peak processing periods and surge capacity needs • Calculate required system capacity (concurrent jobs) • Define storage requirements (JSON, PDFs, audit logs) • Establish monitoring and alerting requirements | Requirements_Specification.docx (including SLAs, volume projections, NFRs) | 0.1 | 3 | BA + Client PM + SME | • Volume projections too conservative (system under-scoped) • SLAs too aggressive given technical constraints • Peak periods exceed capacity (need surge planning) • Historical baseline data not available | • Volume projections defined: current, 6mo, 12mo • Processing time SLA agreed (e.g., <5 min per proposal) • Accuracy SLA defined (e.g., ≥95% extraction accuracy) • Storage requirements calculated based on 2-year retention • Peak capacity requirements identified (surge scenarios) | Not Started
WP0 | 0.5 | Technical Architecture Design | Define target architecture for enterprise scale-up | • Review current POC architecture and identify gaps • Design database schema (proposals, extractions, jobs, audit) • Define API architecture (REST endpoints, authentication) • Design batch processing queue system (Celery/RabbitMQ) • Plan scalability approach (horizontal vs vertical) • Define deployment architecture (cloud vs on-premise) • Design security model (encryption, RBAC, secrets mgmt) • Create infrastructure diagrams (C4 model) • Define monitoring and observability stack • Document technology decisions and tradeoffs | Technical_Architecture_Document.docx + Architecture_Diagrams.pdf (C4 diagrams) | 0.3, 0.4 | 5 | Tech Lead + Architect | • Over-engineering solution (excessive complexity) • Technology choices conflict with client IT standards • Cloud vs on-premise decision delayed or changes • Scalability assumptions invalidated by volume reality | • C4 architecture diagrams (Context, Container, Component) • Database schema defined (ER diagrams with constraints) • API specifications documented (OpenAPI/Swagger) • Deployment model selected and approved by client IT • Security model reviewed and approved • Technology stack ratified (Python, DB, queue, API framework) | Not Started
WP0 | 0.6 | Risk Assessment & Mitigation Planning | Identify project risks and define mitigation strategies | • Conduct risk workshop with stakeholders • Identify technical risks (vendor format changes, AI accuracy) • Identify operational risks (resource availability, SME access) • Identify data risks (quality, volume, security) • Score risks (probability x impact) • Define mitigation strategies for high/medium risks • Create risk register with owners and tracking • Establish risk review cadence (weekly during dev) | Risk_Register.xlsx (with mitigation plans and owners) | 0.1-0.5 | 2 | PM + Tech Lead + Client PM | • New risks emerge during development (inadequate initial assessment) • Risk mitigation strategies inadequate or not executed • Risks not monitored/updated regularly • Scope creep disguised as "risk mitigation" | • Min 15-20 risks identified and documented • All high-impact risks have mitigation plans • Risk owners assigned for each risk • Risk review process established (weekly cadence) • Client sign-off on risk register | Not Started
WP0 | 0.7 | Discovery Exit & Go/No-Go Decision | Review discovery findings and obtain approval to proceed | • Compile discovery findings report • Present findings to client stakeholders • Review scope adjustments (if needed based on findings) • Confirm SLAs and acceptance criteria • Review and approve updated project plan • Obtain sign-off on discovery deliverables (DD1-DD6) • Confirm resource availability for dev phase • Execute Go/No-Go decision | Discovery_Exit_Report.pptx + Signed_Discovery_Acceptance.pdf | 0.1-0.6 | 2 | PM + Tech Lead + Client Sponsor | • Discovery reveals scope significantly larger than estimated • Client requests major scope changes requiring re-estimate • Resource availability conflicts delay dev start • Budget constraints halt project | • All discovery deliverables (DD1-DD6) completed • Client formal acceptance of discovery findings • Scope adjustments (if any) documented and approved • Dev phase work packages validated and approved • Project kickoff scheduled • Payment milestone M0 (10%) approved for invoicing | Not Started
WP1 | 1.1 | Database Design & Implementation | Design and implement PostgreSQL database for proposals, extractions, jobs, audit | • Create detailed database schema (proposals, extractions, jobs, users, audit_log) • Define table relationships and foreign keys • Design indexes for performance (on vendor, date, status fields) • Implement database migration framework (Alembic) • Create seed data for development/testing • Implement database connection pooling (SQLAlchemy) • Create ORM models (SQLAlchemy or Django ORM) • Implement database backup and recovery procedures • Write SQL stored procedures for complex queries • Performance testing with simulated load (1000+ records) | PostgreSQL database + Migration scripts + ORM models + DB_Schema_Documentation.md | WP0 (Discovery) | 8 | Backend Developer + DBA | • Schema design doesn't accommodate future template variations • Performance issues with large JSON fields (extracted_data JSONB) • Migration conflicts when schema changes during dev • Database choice conflicts with client IT standards (e.g., must use MSSQL) | • All tables created with proper constraints and indexes • Foreign key relationships enforced • Migration scripts tested (up and down migrations) • Query performance < 100ms for common operations • Backup/restore tested successfully • Database documented with ER diagrams | Not Started
WP1 | 1.2 | Job Queue System Implementation | Implement Celery + RabbitMQ for asynchronous job processing | • Install and configure RabbitMQ message broker • Set up Celery worker infrastructure • Design job queue architecture (task routing, priorities) • Implement extraction job task (celery task) • Implement job status tracking (pending, in_progress, completed, failed) • Create job retry logic with exponential backoff • Implement job result storage (database + file system) • Set up Flower for queue monitoring (web UI) • Configure worker concurrency and resource limits • Implement dead letter queue for failed jobs • Write queue health check and monitoring scripts | Celery + RabbitMQ infrastructure + Job management API + Queue_Setup_Documentation.md | 1.1 | 7 | Backend Developer + DevOps | • RabbitMQ configuration complex for team unfamiliar with it • Worker crashes under high load (memory leaks) • Job queue fills up faster than processing (backlog) • Network issues between queue and workers (distributed setup) | • RabbitMQ running and accessible • Celery workers processing jobs successfully • Job status tracked in database in real-time • Failed jobs automatically retried (max 3 attempts) • Flower dashboard shows queue metrics • Load tested: 20 concurrent jobs processed successfully | Not Started
WP1 | 1.3 | Configuration Management System | Implement environment-based configuration management | • Create config file structure (config/dev.py, config/prod.py, etc.) • Implement environment detection (.env file + env variables) • Migrate hardcoded API keys to environment variables • Implement secrets management (AWS Secrets Manager or HashiCorp Vault) • Create configuration validation on startup • Document all configuration parameters • Implement feature flags for gradual rollout • Create configuration template files (.env.example) • Implement configuration reload without restart (where possible) • Add configuration audit logging (who changed what when) | Config management system + Secrets vault integration + Configuration_Guide.md | - | 4 | Backend Developer | • Secrets accidentally committed to Git (hardcoded API keys) • Environment-specific bugs due to config differences • Configuration drift between environments • Secrets vault access issues in production | • No hardcoded secrets in codebase (Git history cleaned) • All environments (dev, staging, prod) using env-specific configs • Secrets rotated without code changes • Configuration validation prevents startup with invalid config • Config changes logged to audit trail | Not Started
WP1 | 1.4 | Structured Logging Infrastructure | Implement centralized structured logging with rotation and monitoring | • Implement structured logging (JSON format with context) • Set up log rotation policies (size-based + time-based) • Configure log levels per module (DEBUG, INFO, WARNING, ERROR) • Implement correlation IDs for request tracing • Set up centralized log aggregation (ELK stack or CloudWatch) • Create log parsing and alerting rules • Implement PII masking in logs (no sensitive data logged) • Add performance metrics logging (processing times, API calls) • Create log retention policies (30 days debug, 1 year audit) • Set up log monitoring dashboards | Logging framework + Log aggregation system + Logging_Standards.md | - | 5 | Backend Developer + DevOps | • Log volume exceeds storage capacity (need compression/archival) • PII accidentally logged (compliance violation) • Logs don't correlate across distributed workers • Log aggregation system performance bottleneck | • All modules using structured logging (JSON format) • Logs include: timestamp, level, correlation_id, module, message, context • Log rotation working (max 100MB per file, 30-day retention) • PII masking validated (no SSN, credit cards in logs) • Centralized dashboard shows logs across all workers • Alerting configured for ERROR and CRITICAL logs | Not Started
WP1 | 1.5 | API Framework Setup | Build RESTful API foundation with FastAPI | • Set up FastAPI application structure • Implement API authentication (JWT tokens or API keys) • Create API documentation (OpenAPI/Swagger auto-generated) • Implement request validation (Pydantic models) • Add API rate limiting and throttling • Implement CORS configuration • Create health check endpoints (/health, /ready) • Implement API versioning strategy (v1, v2 paths) • Add request/response logging middleware • Set up API testing framework (pytest + httpx) • Implement error handling and standard error responses | FastAPI application + API documentation + API_Standards.md | 1.1, 1.3 | 6 | Backend Developer | • API design doesn't meet client integration needs • Authentication mechanism too complex for clients • Rate limiting too restrictive (blocks legitimate use) • API breaking changes during development | • FastAPI app running and accessible • Swagger UI accessible at /docs endpoint • Authentication working (valid tokens accepted, invalid rejected) • All endpoints return standard error format • Health check returns 200 with system status • API tested with Postman/httpx (test collection provided) | Not Started
WP2 | 2.1 | Bulk Import & Queue Management | Build system to ingest multiple proposals and queue for processing | • Implement directory watcher for auto-ingestion (watchdog library) • Create bulk upload API endpoint (multi-file upload) • Implement file validation (format, size, virus scan) • Build proposal metadata extraction (vendor detection, date parsing) • Implement automatic vendor classification (FIS, JH, CSI detection) • Create queue prioritization logic (urgent vs normal) • Implement duplicate detection (hash-based) • Build proposal staging area (uploaded files before processing) • Create batch submission API (submit 20+ files at once) • Implement queue status API (how many jobs in queue) • Add batch validation reporting (which files accepted/rejected) | Bulk import system + Queue management API + Import_User_Guide.md | WP1 (DB, Queue) | 7 | Backend Developer | • Large file uploads fail or timeout (>50MB PDFs) • Virus scanning delays ingestion (performance bottleneck) • Vendor auto-detection fails on ambiguous documents • Queue fills faster than workers process (backlog grows) | • Bulk upload handles 20+ files in single request • Vendor auto-detection ≥90% accuracy (tested on samples) • Duplicate files rejected before queueing • Invalid files rejected with clear error messages • Queue prioritization working (urgent jobs processed first) • Directory watcher auto-ingests files from hot folder | Not Started
WP2 | 2.2 | Parallel Worker Pool Implementation | Implement multi-worker system for concurrent proposal processing | • Configure Celery worker pool (4-8 concurrent workers) • Implement worker health monitoring and auto-restart • Set up worker resource limits (memory, CPU) • Implement graceful worker shutdown (finish current job) • Create worker scaling strategy (manual or auto-scaling) • Implement job timeout handling (max 10 min per job) • Add worker performance metrics collection • Implement worker task routing (by vendor or complexity) • Set up worker-specific logging • Create worker management commands (start, stop, scale) • Implement job cancellation (kill running job) | Worker pool infrastructure + Scaling playbook + Worker_Operations_Guide.md | 1.2 (Job Queue) | 6 | Backend Developer + DevOps | • Workers crash under load (memory leaks, API timeouts) • Uneven load distribution (some workers idle, others overloaded) • Worker scaling too slow (can't handle surge) • Jobs timeout on complex proposals (need tuning) | • Min 4 workers processing jobs concurrently • Worker crashes auto-restart within 30 seconds • Jobs distributed evenly across workers • Worker resource usage monitored (CPU, memory) • Timeout configured (jobs fail after 10 min) • Load tested: 20 proposals processed in <30 min (avg 90 sec each) | Not Started
WP2 | 2.3 | Error Handling & Retry Logic | Implement comprehensive error handling with intelligent retry | • Define error taxonomy (transient vs permanent errors) • Implement retry logic with exponential backoff (3 attempts) • Create dead letter queue for permanent failures • Implement error notification system (email/Slack) • Build error detail capture (stack traces, context) • Create error recovery procedures documentation • Implement manual retry from UI (for dead letter queue) • Add error rate alerting (>10% failure rate) • Implement partial success handling (some items extracted) • Create error analytics dashboard (failure patterns) • Build automatic error categorization (AI timeout, PDF corrupt, etc.) | Error handling framework + Dead letter queue + Error_Playbook.md | 2.1, 2.2 | 5 | Backend Developer | • Retry logic creates infinite loops (retry permanently failing job) • Error notifications too noisy (alert fatigue) • Dead letter queue grows unbounded (no cleanup) • Transient errors misclassified as permanent (no retry) | • Transient errors auto-retry (max 3 attempts) • Permanent failures move to dead letter queue • Error notifications sent for all failures (email or Slack) • Error details logged with full context • Dead letter queue UI allows manual retry • Tested: API timeout retries, corrupt PDF fails permanently | Not Started
WP2 | 2.4 | Progress Tracking & Reporting | Real-time progress visibility for batch jobs | • Implement job progress tracking (0-100% for each job) • Create batch progress API (overall batch completion) • Build WebSocket for real-time progress updates • Implement stage-based progress (uploading, queued, extracting, QA, complete) • Create progress event logging (stage transitions) • Build progress dashboard UI (simple HTML + JS) • Implement ETA calculation (based on average processing time) • Add throughput metrics (proposals per hour) • Create batch summary report (X of Y complete, Z failed) • Implement progress notifications (batch 50% done, batch complete) | Progress tracking API + Real-time dashboard + Progress_API_Docs.md | 2.2 | 6 | Full Stack Developer | • WebSocket connection drops (progress updates lost) • ETA calculation inaccurate (wide variance in processing time) • Progress updates too frequent (performance overhead) • Progress tracking doesn't work across distributed workers | • Real-time progress visible in dashboard (updates every 5 sec) • Batch progress API returns: total, completed, failed, in_progress • ETA displayed (based on rolling average) • Progress notifications sent at 50% and 100% • Tested: 20-proposal batch tracked from start to finish • WebSocket reconnects automatically on disconnect | Not Started
WP3 | 3.1 | Template Registry & Versioning | Build system to manage multiple TCO template variants | • Design template registry database schema • Implement template upload and storage • Create template versioning system (v1.0, v1.1, v2.0) • Build template metadata extraction (column mappings, formulas) • Implement template validation (required fields present) • Create template diff tool (compare versions) • Implement template activation/deactivation (which is current) • Build template selection API (get template by ID or criteria) • Create template audit log (who uploaded, when, changes) • Implement template export/import (for backup/migration) • Build template testing framework (validate mappings work) | Template registry system + Versioning API + Template_Management_Guide.md | WP1 (Database) | 7 | Backend Developer + BA | • Template mapping extraction fails on complex templates • Version conflicts when multiple templates updated • Template validation too strict (rejects valid templates) • Backward compatibility broken when template structure changes | • Template registry stores ≥3 template variants • Template versioning working (can rollback to previous version) • Template metadata extracted automatically on upload • Template diff shows field mapping changes • Audit log tracks all template changes • Tested: upload template, activate, generate TCO output | Not Started
WP3 | 3.2 | Dynamic Field Mapping Engine | Build flexible field-to-cell mapping system | • Design mapping configuration schema (JSON or YAML) • Implement field mapping parser (config → execution plan) • Create mapping rule engine (conditional mappings) • Build cell coordinate calculator (dynamic row/column) • Implement formula template engine (parameterized formulas) • Create data transformation layer (format conversions) • Implement mapping validation (all fields mapped) • Build mapping test framework (verify mappings correct) • Create mapping versioning (tied to template version) • Implement fallback mappings (for missing fields) • Build mapping documentation generator | Mapping engine + Configuration schema + Mapping_Configuration_Guide.md | 3.1 | 8 | Developer + Data Engineer | • Mapping configuration too complex for non-developers • Dynamic cell calculation errors (off-by-one) • Formula templating doesn't support all Excel formulas • Mapping changes break existing extractions | • Mapping config supports: fixed cells, dynamic rows, conditional logic • Formula templates support: SUM, IF, VLOOKUP, INDEX/MATCH • Mapping validation catches: missing fields, invalid cells • Mapping tested on 3+ template variants successfully • Fallback mappings prevent failures from missing fields • Mapping documentation auto-generated from config | Not Started
WP3 | 3.3 | Template Auto-Detection Logic | Automatically match proposal to correct TCO template | • Define template selection criteria (vendor, client, date, proposal type) • Implement rule-based template matching • Build template scoring algorithm (best match) • Create template override mechanism (manual selection) • Implement template recommendation system • Add template selection logging (why this template chosen) • Build template selection testing framework • Create template selection API • Implement client-specific template routing • Build default template fallback (if no match) • Add template selection audit trail | Template detection engine + Selection API + Template_Selection_Logic.md | 3.1, 3.2 | 5 | Developer | • Auto-detection selects wrong template (poor matching logic) • No suitable template found for proposal (need fallback) • Client-specific routing rules conflict • Template selection logic too rigid (can't handle edge cases) | • Template detection ≥95% accuracy (tested on sample proposals) • Selection logic considers: vendor, client, date, custom rules • Manual override available via API • Selection rationale logged (why template X chosen) • Tested: proposals from 3 vendors route to correct templates • Fallback to default template if no match | Not Started
WP3 | 3.4 | Template Management UI | Web interface for template configuration (non-developer) | • Design template management UI wireframes • Implement template upload interface • Build visual mapping configurator (point-and-click) • Create template preview (see mapping results) • Implement template testing tool (upload sample, see output) • Build template comparison view (side-by-side) • Create template activation/deactivation controls • Implement template version history view • Build template documentation viewer • Add template export/import UI • Implement user permissions (who can edit templates) | Template management web UI + User_Guide.pdf | 3.1, 3.2, 3.3 | 10 | Full Stack Developer + UX Designer | • UI too complex for business users (requires training) • Visual mapping configurator buggy (hard to use) • Template preview doesn't match actual output • UI performance slow with large templates | • Template upload via drag-and-drop • Visual mapping configurator (map fields to cells without code) • Template preview shows sample TCO output • Template testing: upload proposal + template → see result • Version history shows all template changes • Tested: non-developer user can upload and configure template | Not Started
WP4 | 4.1 | Bulk Historical Import Utility | CLI tool for mass import of historical proposals | • Build CLI tool for directory scanning • Implement recursive folder traversal • Create file filtering (by extension, date, size) • Build batch upload (chunks of 50 files) • Implement progress tracking (X of Y uploaded) • Add dry-run mode (preview without uploading) • Create import summary report (files uploaded, skipped, failed) • Implement resume capability (continue interrupted import) • Build import validation (check files before upload) • Add import scheduling (throttle uploads to avoid overload) • Create import logging (detailed activity log) | Historical import CLI tool + Import_Tool_User_Guide.md | WP2 (Bulk Import) | 5 | Developer | • Import overwhelms system (too many files at once) • Network failures interrupt large imports (need resume) • File filtering misses important files (wrong criteria) • Import tool doesn't handle edge cases (special characters in filenames) | • CLI scans directory and subdirectories • Dry-run mode shows what would be imported • Batch upload (50 files per API call) working • Resume capability tested (interrupt and restart) • Import report shows: uploaded, skipped (duplicates), failed • Tested: import 100+ historical files successfully | Not Started
WP4 | 4.2 | Document Classification & Vendor Detection | Automatically identify vendor and proposal type | • Build vendor detection algorithm (keyword matching, logo detection) • Implement format detection (Word, Excel, PDF, scanned image) • Create proposal type classification (pricing vs terms vs summary) • Build confidence scoring for classification • Implement manual classification override • Create classification training data collection • Build classification validation (manual review sample) • Implement classification reporting (accuracy metrics) • Add classification caching (store results) • Create classification API • Build classification testing framework | Classification engine + Vendor detection API + Classification_Guide.md | 4.1 | 7 | ML Engineer / Developer | • Vendor detection fails on older/non-standard formats • Scanned images too low quality (OCR fails) • Classification accuracy too low (<90%) • Vendor branding changes over time (detection breaks) | • Vendor detection ≥90% accuracy (tested on samples) • Format detection 100% accurate (Word, Excel, PDF, image) • Proposal type classification ≥85% accuracy • Confidence scores provided for all classifications • Manual override available for incorrect classifications • Tested: classify 50 historical proposals, validate results | Not Started
WP4 | 4.3 | Legacy Format Handlers | Support for older document formats (.doc, Excel 2003, scanned PDFs) | • Implement .doc (Word 97-2003) reader • Add Excel 2003 (.xls) support • Build scanned PDF OCR pipeline (Tesseract) • Implement image enhancement (deskew, denoise) for OCR • Create legacy format conversion (convert to modern format first) • Build format-specific extraction strategies • Implement legacy format testing • Create fallback extraction (hybrid OCR + AI) • Build legacy format validation • Add legacy format handling documentation • Implement legacy format performance optimization | Legacy format handlers + OCR pipeline + Legacy_Format_Guide.md | 4.2 | 8 | Developer + ML Engineer | • OCR accuracy too low on poor-quality scans (<80%) • Legacy formats too corrupted to read • OCR processing too slow (minutes per document) • Legacy format extraction accuracy significantly lower than modern | • .doc and .xls files processed successfully • OCR accuracy ≥85% on clean scans (tested with samples) • Image enhancement improves OCR accuracy by ≥10% • Legacy format processing time <2x modern formats • Fallback to hybrid extraction when OCR confidence <80% • Tested: process 20 legacy format proposals | Not Started
WP4 | 4.4 | De-duplication & Historical Analysis | Identify duplicate proposals and analyze historical pricing trends | • Implement file hash-based de-duplication • Build content similarity detection (fuzzy matching) • Create duplicate resolution workflow (keep which version) • Implement historical pricing database • Build pricing trend analysis (vendor X over time) • Create anomaly detection (unusually high/low pricing) • Implement benchmarking reports (compare to historical average) • Build historical data visualization dashboard • Create data quality metrics (completeness, accuracy over time) • Implement historical data export (for analysis) • Build historical insights API | De-duplication engine + Historical analytics + Historical_Analysis_Dashboard | 4.1, 4.2 | 6 | Data Engineer + Analyst | • De-duplication misses duplicates (different file names) • Similarity detection too sensitive (flags non-duplicates) • Historical data quality too poor for meaningful analysis • Pricing trends don't provide actionable insights | • Hash-based de-duplication catches exact duplicates • Similarity detection ≥90% accuracy (tested on sample duplicates) • Duplicate resolution workflow allows manual selection • Historical pricing database populated with all extractions • Trend analysis shows pricing changes over time (by vendor) • Anomaly detection flags outliers (>2 std dev from mean) | Not Started
WP5 | 5.1 | Review Queue Backend | Build exception queue for manual review items | • Design review queue database schema (review items, comments, approvals) • Implement review queue API (get items, update, approve, reject) • Build review assignment logic (round-robin, skill-based) • Create review item detail view (show extraction + source) • Implement review item prioritization (by confidence, urgency) • Build review comment system (threaded discussions) • Implement review item locking (one user at a time) • Create review item history (all changes tracked) • Build review SLA tracking (time in queue) • Implement review queue metrics (throughput, aging) • Create review queue notifications (new items, SLA breach) | Review queue backend + API + Review_Queue_Schema.md | WP1 (Database), WP2 (Bucket Routing) | 7 | Backend Developer | • Review queue fills faster than reviewers can process • Review assignment logic unfair (uneven distribution) • Review item locking causes conflicts (user loses work) • SLA tracking doesn't account for weekends/holidays | • Review queue stores items from Bucket 2 (70-89% confidence) • API supports: get queue, assign item, update, approve, reject • Review assignment distributes items evenly • Item locking prevents concurrent edits • Review history tracks all changes with timestamps • SLA alerts trigger when item >24 hours in queue | Not Started
WP5 | 5.2 | Web-based Review UI | Build intuitive review interface for non-technical users | • Design review UI wireframes and mockups • Implement review dashboard (queue overview, My Items) • Build review item detail page (side-by-side: extraction vs source) • Create inline editing (edit fields directly in UI) • Implement source document viewer (PDF, Word, Excel preview) • Build confidence indicator visualization (color-coded) • Create bulk actions (approve all, assign multiple) • Implement keyboard shortcuts (faster navigation) • Build review commenting UI (add notes, @mention) • Create review history timeline view • Implement review filters and search (by vendor, date, status) • Add review analytics (my throughput, avg review time) | Review web UI + User_Guide.pdf + UI_Mockups.pdf | 5.1 | 12 | Full Stack Developer + UX Designer | • UI too complex (requires extensive training) • Source document preview doesn't work for all formats • Inline editing buggy (data loss) • UI performance slow with large documents (>100 line items) | • Review dashboard shows: queue count, my items, completed today • Item detail shows extraction side-by-side with source • Inline editing allows field updates without page reload • Source preview works for: PDF, Word, Excel • Confidence indicators color-coded (red <70%, yellow 70-89%, green ≥90%) • Tested: non-technical user can review and approve item in <5 min | Not Started
WP5 | 5.3 | Approval Workflow & State Machine | Implement review state machine and approval routing | • Design approval state machine (draft, in_review, approved, rejected) • Implement state transitions with validation • Build multi-level approval (reviewer → manager) • Create approval delegation (assign to someone else) • Implement approval expiration (auto-escalate after timeout) • Build approval notification system (email/Slack) • Create approval audit trail (who approved when) • Implement conditional routing (high-value items → manager) • Build approval rollback (undo approval) • Create approval reporting (approval rates, bottlenecks) • Implement approval SLA tracking | Approval workflow engine + State machine + Approval_Workflow_Guide.md | 5.2 | 6 | Backend Developer + BA | • State machine too complex (hard to understand) • Approval bottlenecks (manager becomes blocker) • Notification fatigue (too many approval emails) • Approval delegation misused (bypass approvals) | • State machine enforces valid transitions only • Multi-level approval working (item routed to manager if >$1M) • Approval delegation tracked in audit trail • Auto-escalation after 48 hours in review • Notifications sent: on assignment, on approval, on rejection • Tested: approval workflow from submission to final approval | Not Started
WP5 | 5.4 | Feedback Loop & Active Learning | Capture manual corrections to improve extraction accuracy | • Implement correction tracking (original vs corrected values) • Build correction categorization (field type, error type) • Create correction analytics (most frequently corrected fields) • Implement prompt refinement based on corrections • Build vendor-specific learning (cache corrections per vendor) • Create correction-based re-training pipeline • Implement confidence threshold tuning (adjust based on accuracy) • Build correction suggestion system (learn patterns) • Create correction reporting dashboard (accuracy improvements) • Implement A/B testing framework (test prompt changes) • Build correction export (for external analysis) | Feedback loop system + Learning pipeline + Feedback_Loop_Guide.md | 5.3 | 8 | ML Engineer + Developer | • Correction data too sparse (not enough to learn from) • Learning pipeline doesn't improve accuracy (changes ineffective) • Prompt changes break existing accurate extractions • A/B testing framework too complex to use | • All corrections captured: field, original, corrected, reason • Correction analytics show: most common error types • Prompt refinement improves accuracy by ≥5% (tested on validation set) • Vendor-specific cache stores corrections (90-day TTL) • A/B testing framework allows comparing 2 prompt versions • Tested: 20 corrections → prompt update → re-extract → accuracy improvement | Not Started
WP6 | 6.1 | Real-time Status Dashboard | Build operations dashboard for system health and job status | • Design dashboard wireframes (system health, jobs, queues) • Implement dashboard backend API (metrics aggregation) • Build real-time metrics display (WebSocket) • Create system health indicators (DB, queue, workers, API) • Implement job status overview (total, in progress, completed, failed) • Build queue depth visualization (jobs waiting) • Create worker status display (active, idle, crashed) • Implement recent activity feed (last 50 jobs) • Build error rate trending (last 24 hours) • Create throughput metrics (proposals per hour) • Implement dashboard refresh controls (auto-refresh, manual) • Add dashboard filters (by vendor, date range, status) | Operations dashboard + Metrics API + Dashboard_User_Guide.md | WP2 (Processing), WP1 (Logging) | 8 | Full Stack Developer | • Dashboard performance slow with large datasets • Real-time updates don't scale (too many WebSocket connections) • Metrics aggregation queries slow down database • Dashboard shows stale data (caching issues) | • Dashboard shows: system health, job counts, queue depth, worker status • Real-time updates (metrics refresh every 5 seconds) • System health checks: DB (green/red), Queue (green/yellow/red), Workers (count) • Job status: total today, completed, failed, in progress • Error rate trend (line chart last 24 hours) • Tested: dashboard accurate during 20-proposal batch processing | Not Started
WP6 | 6.2 | Notification & Alerting System | Email and Slack notifications for critical events | • Implement email notification system (SMTP) • Build Slack integration (webhook or bot) • Create notification templates (job complete, job failed, SLA breach) • Implement notification preferences (user settings) • Build notification throttling (avoid alert fatigue) • Create notification channels (email, Slack, SMS) • Implement escalation rules (critical errors → manager) • Build notification scheduling (business hours only) • Create notification testing tool (send test alerts) • Implement notification audit log (all sent notifications) • Build notification digest (daily summary email) • Create notification customization (per user or team) | Notification system + Slack bot + Email templates + Notification_Guide.md | 6.1 | 6 | Backend Developer | • Email delivery issues (SMTP server down, spam filters) • Slack webhook rate limits (too many notifications) • Alert fatigue (too many notifications ignored) • Notification preferences too complex (users confused) | • Email notifications working (job complete, job failed) • Slack notifications posted to channel (with job details) • Notification throttling (max 1 alert per 5 min for same error) • User preferences allow: enable/disable by event type • Escalation working (critical error → manager email) • Tested: simulate job failure → email and Slack notification sent | Not Started
WP6 | 6.3 | Analytics & Standard Reports | Pre-built reports for common business questions | • Design report requirements (with client stakeholders) • Implement report data models (aggregations, summaries) • Build Extraction Accuracy Report (by vendor, over time) • Create Processing Volume Report (proposals per day/week/month) • Implement Review Queue Metrics Report (SLA compliance, throughput) • Build Cost Analysis Report (API costs, processing costs) • Create User Activity Report (who processed what) • Implement Vendor Comparison Report (accuracy by vendor) • Build Error Analysis Report (common failure patterns) • Create report scheduling (auto-generate weekly/monthly) • Implement report export (PDF, Excel, CSV) • Build report API (programmatic access) • Create custom report builder (drag-and-drop) | Report library + Report scheduler + Custom report builder + Reports_Catalog.pdf | 6.1, WP5 (Review) | 10 | Data Engineer + Full Stack Developer | • Report requirements change during development • Report queries too slow (need optimization) • Custom report builder too limited (can't answer all questions) • Report scheduling overwhelms system (too many concurrent reports) | • Min 7 standard reports implemented (listed above) • Reports generated on-demand (< 30 seconds) • Report scheduling working (weekly email with PDF) • Report export to: PDF, Excel, CSV • Custom report builder allows: filter, group by, aggregate • Tested: generate all reports with real data, validate accuracy | Not Started
WP6 | 6.4 | Audit Trail Enhancement | Comprehensive audit logging for compliance and debugging | • Design audit trail schema (events, actors, timestamps, changes) • Implement audit logging for all critical operations • Create audit log API (query, filter, export) • Build audit log UI (searchable, filterable) • Implement data lineage tracking (proposal → extraction → TCO) • Create change tracking (who changed what when) • Build audit log retention policy (7 years) • Implement audit log export (for compliance) • Create audit log integrity verification (tamper-proof) • Build audit log analytics (user activity patterns) • Implement audit log search (full-text search) • Create audit log reporting (compliance reports) | Enhanced audit system + Audit UI + Audit_Log_Specification.md | WP1 (Logging), WP5 (Review) | 7 | Backend Developer + Security Engineer | • Audit log volume excessive (storage costs) • Audit queries too slow (need indexing) • Audit log doesn't capture all required events • Audit log retention conflicts with storage limits | • All critical operations logged: upload, extract, review, approve, export • Audit log includes: timestamp, user, action, object, before/after values • Data lineage tracked (proposal ID → extraction ID → TCO file) • Audit UI allows search and filter (by user, date, action) • Audit log export to CSV (for compliance reporting) • Tested: complete audit trail from proposal upload to TCO output | Not Started
WP7 | 7.1 | Unit Test Expansion (80% Coverage) | Expand unit test coverage across all modules | • Audit current test coverage (generate coverage report) • Identify untested modules and functions • Write unit tests for extractors (fis, jh, pdf) • Write unit tests for mappers (schema normalization) • Write unit tests for writers (TCO Excel generation) • Write unit tests for QA validation • Write unit tests for API endpoints • Write unit tests for queue and workers • Implement test fixtures and mocks (sample proposals) • Create test data generators (synthetic proposals) • Set up test coverage enforcement (CI fails if <80%) • Implement mutation testing (test quality validation) | Expanded test suite + Coverage report + Test_Documentation.md | WP1-WP6 (All modules implemented) | 10 | QA Engineer + Developers | • Test coverage metric achieved but tests low quality (not testing real scenarios) • Mocking too extensive (tests don't reflect real behavior) • Test maintenance burden (tests break on every change) • Test execution time too long (slow CI pipeline) | • Unit test coverage ≥80% (lines of code) • All critical paths covered (extraction, mapping, output) • Test execution time < 5 minutes (for unit tests) • All tests passing (0 failures) • Test documentation includes: how to run, how to add tests • Coverage report generated automatically in CI | Not Started
WP7 | 7.2 | Integration Testing | End-to-end integration tests across system components | • Design integration test scenarios (happy path, error paths) • Set up integration test environment (test DB, test queue) • Write E2E test: upload proposal → extract → output TCO • Test multi-vendor scenarios (FIS, JH, CSI in one batch) • Test review workflow (item goes to queue → reviewed → approved) • Test template selection (correct template chosen) • Test error handling (retry, dead letter queue) • Test API integrations (all endpoints) • Test database integrations (CRUD operations) • Test queue integrations (job submission → completion) • Implement integration test fixtures (sample data) • Create integration test documentation | Integration test suite + Test environment + Integration_Test_Plan.md | 7.1 | 8 | QA Engineer + Developer | • Integration test environment drift from production • Tests flaky (pass sometimes, fail others) • Test data setup complex and brittle • Integration tests too slow (minutes per test) | • Min 15 integration test scenarios implemented • E2E test (upload → extract → TCO) passing for 3 vendors • Review workflow tested end-to-end • Error handling scenarios tested (API timeout, corrupt file) • Integration tests run in isolated environment (no prod data) • All integration tests passing (0 failures) | Not Started
WP7 | 7.3 | Volume & Performance Testing | Stress test with 20+ proposals, measure performance | • Design volume test plan (20, 50, 100 proposals) • Create performance test dataset (varied complexity) • Set up performance test environment (production-like) • Execute 20-proposal stress test (baseline) • Measure processing times (avg, p95, p99) • Measure system resource usage (CPU, memory, disk) • Identify performance bottlenecks (profiling) • Optimize critical paths (database queries, API calls) • Re-test after optimizations • Test concurrent processing (4 workers, 8 workers) • Measure API throughput (requests per second) • Create performance baseline documentation • Test surge scenario (100 proposals submitted at once) | Performance test report + Optimization recommendations + Load_Test_Results.pdf | 7.2 | 6 | QA Engineer + Performance Engineer | • System performance inadequate under load • Bottlenecks not identified (poor profiling) • Optimizations don't improve performance significantly • Test environment doesn't match production (misleading results) | • 20-proposal batch processed in <30 minutes (avg 90 sec/proposal) • System stable under load (no crashes, memory leaks) • Resource usage acceptable (CPU <80%, memory <16GB) • API response times <500ms (p95) • Concurrent processing scales (8 workers = 2x throughput vs 4) • Performance report documents: avg time, p95, p99, resource usage | Not Started
WP7 | 7.4 | User Acceptance Testing (UAT) | Client validates system meets requirements | • Create UAT test plan (scenarios, acceptance criteria) • Prepare UAT environment (production-like) • Create UAT test data (real proposals from client) • Conduct UAT training session (how to use system) • Execute UAT scenarios with client users • Document UAT findings (bugs, issues, enhancements) • Triage and fix UAT issues (P0, P1, P2) • Re-test fixed issues with client • Collect client feedback (usability, features) • Obtain UAT sign-off (formal acceptance) • Create UAT report (test results, issues, sign-off) • Transition to production (deployment plan) | UAT test plan + UAT report + UAT sign-off document + Go-live readiness checklist | 7.3 | 10 | PM + QA + Client Users (3-5) | • Client not available for UAT (delays) • UAT uncovers major issues (requires rework) • Client expectations mismatch (feature gaps) • UAT environment issues (not production-like) | • UAT test plan covers all major user scenarios (min 20 scenarios) • Client users trained (min 3 users) • All P0 and P1 UAT issues resolved • Client formal sign-off obtained (signed document) • UAT report documents: scenarios tested, pass/fail, issues, resolutions • Go-live readiness checklist 100% complete | Not Started
WP8 | 8.1 | Technical Documentation | Architecture, API, and developer documentation | • Write architecture documentation (C4 diagrams, system overview) • Document database schema (ER diagrams, table descriptions) • Create API documentation (OpenAPI/Swagger, endpoint details) • Write developer setup guide (local dev environment) • Document code architecture (module overview, design patterns) • Create deployment guide (production setup) • Write configuration reference (all settings explained) • Document integration points (external systems) • Create troubleshooting guide (common issues, solutions) • Write security documentation (authentication, encryption, secrets) • Document testing framework (how to run, how to add tests) • Create code contribution guide (standards, PR process) | Technical_Documentation/ folder (Architecture, API, Developer guides) + ReadTheDocs site | WP7 (Testing complete) | 8 | Tech Writer + Tech Lead | • Documentation becomes outdated quickly (code changes) • Documentation too technical (hard for new developers) • Documentation incomplete (missing critical info) • Documentation not maintained (no ownership) | • Architecture documentation includes: C4 diagrams, data flow, technology stack • API documentation auto-generated from code (Swagger UI) • Developer setup guide tested (new dev can set up in <2 hours) • Deployment guide tested (can deploy to new environment) • Troubleshooting guide covers top 10 common issues • Documentation hosted (ReadTheDocs or internal wiki) | Not Started
WP8 | 8.2 | Operations Manual | Daily operations procedures for support team | • Write operations overview (roles, responsibilities) • Create daily operations checklist (health checks) • Document batch processing procedures (how to submit, monitor) • Write review queue procedures (how to review, approve) • Create incident response procedures (errors, outages) • Document backup and recovery procedures • Write monitoring procedures (dashboard, alerts) • Create user management procedures (add, remove, permissions) • Document template management procedures (upload, configure) • Write report generation procedures (schedule, export) • Create escalation procedures (when to escalate) • Document common support tasks (FAQ for support team) | Operations_Manual.pdf + Runbook/ folder (step-by-step procedures) | 8.1 | 6 | Tech Writer + Operations Lead | • Operations manual too generic (not specific to this system) • Procedures not tested (don't work in practice) • Manual too long (support team won't read) • Manual not updated when system changes | • Operations manual covers: daily tasks, incident response, common issues • Runbook includes: step-by-step procedures with screenshots • Daily checklist tested (ops team can execute) • Incident response tested (simulate outage, follow procedures) • Escalation procedures define: when to escalate, who to contact • Support team trained on operations manual | Not Started
WP8 | 8.3 | End-User Documentation | User guides for business users | • Write user guide (getting started, core workflows) • Create video tutorials (screen recordings with narration) • Document batch upload workflow (with screenshots) • Write review workflow guide (how to review, approve) • Create template management guide (for template admins) • Document report generation (how to generate, schedule) • Write FAQ (common questions, troubleshooting) • Create quick reference guide (1-page cheat sheet) • Document keyboard shortcuts and tips • Write release notes (what's new) • Create context-sensitive help (tooltips, in-app help) • Build user documentation portal (searchable) | User_Guide.pdf + Video tutorials + FAQ + Help portal | 8.1 | 7 | Tech Writer + UX Designer | • User guide too technical (users confused) • Videos become outdated (UI changes) • Documentation doesn't match user mental models • Help portal not discoverable (users don't find it) | • User guide covers: upload, review, approve, reports (with screenshots) • Min 5 video tutorials (3-5 min each): upload, review, templates, reports, FAQ • FAQ answers top 20 user questions • Quick reference guide (1-page PDF) • Help portal searchable and linked from UI • User guide tested with non-technical users (feedback incorporated) | Not Started
WP8 | 8.4 | Knowledge Transfer & Training | Training sessions for client team | • Design training curriculum (admin, user, developer tracks) • Create training materials (slides, exercises, datasets) • Conduct administrator training (system config, user mgmt) • Conduct end-user training (upload, review, reports) • Conduct developer training (code overview, how to extend) • Create hands-on exercises (practice scenarios) • Conduct Q&A sessions (answer questions) • Record training sessions (for future reference) • Create training certification (knowledge check) • Provide post-training support (office hours) • Document training feedback (improvements) • Create training calendar (ongoing education) | Training materials + Recorded sessions + Training certification + Training_Report.pdf | 8.1, 8.2, 8.3 | 6 | Trainer + Tech Lead + PM | • Training too rushed (not enough time) • Client team not available (scheduling conflicts) • Training too technical (users overwhelmed) • Training doesn't stick (no reinforcement) | • Min 3 training tracks delivered: admin (4 hours), user (2 hours), developer (4 hours) • Training materials include: slides, hands-on exercises, sample data • All sessions recorded and accessible • Min 80% of trainees pass certification (knowledge check) • Post-training support provided (2 weeks office hours) • Training feedback collected and positive (avg ≥4/5) | Not Started

## Risk Register
ID | Risk Description | Probability | Impact | Score | Mitigation | Owner | Status
R1 | Historical documents in unknown formats | Medium | High | High | Early discovery phase with sample analysis | Tech Lead | Open
R2 | TCO template variations more complex than expected | Medium | Medium | Medium | Flexible mapping engine with fallback options | Developer | Open
R3 | Volume exceeds capacity | Low | Medium | Low | Scalable architecture with parallel processing | Tech Lead | Open
R4 | Key resource unavailable | Medium | Medium | Medium | Cross-training; documentation | PM | Open
R5 | Client SME availability | Medium | High | High | Early scheduling; async communication | PM | Open
R6 | Integration dependencies | Low | Medium | Low | Modular design with clear APIs | Tech Lead | Open
R7 | Performance bottlenecks | Medium | Medium | Medium | Early performance testing; optimization sprints | Developer | Open
R8 | Scope creep | Medium | High | High | Change control process; clear SOW | PM | Open

## Acceptance Criteria
ID | Type | Criteria | Target | Validation Method | Status
AC1 | Functional | System processes 20+ proposals per month | - | Volume test with real proposals | Not Tested
AC2 | Functional | Historical proposals imported with >90% success rate | >90% | Batch processing report | Not Tested
AC3 | Functional | All TCO template variants supported via configuration | 100% | Template coverage test | Not Tested
AC4 | Functional | Exception queue enables manual review with resolution tracking | - | Workflow walkthrough | Not Tested
AC5 | Functional | Monitoring dashboard shows real-time status and alerts | - | UI demonstration | Not Tested
PA1 | Performance | Single proposal processing time | < 2 minutes | Timing test | Not Tested
PA2 | Performance | Batch of 20 proposals | < 30 minutes | Batch timing test | Not Tested
PA3 | Performance | Dashboard response time | < 3 seconds | UI response test | Not Tested
PA4 | Performance | System availability | 99% | Uptime monitoring | Not Tested
QA1 | Quality | Extraction accuracy (auto-accepted) | > 95% | Accuracy report | Not Tested
QA2 | Quality | Overall processing success rate | > 98% | Processing report | Not Tested
QA3 | Quality | Zero data loss or corruption | 100% | Data integrity check | Not Tested
QA4 | Quality | Complete audit trail for all outputs | 100% | Audit log review | Not Tested